Annterra Pharma

Response to Request for Proposal

Allerveo 180mg Tablet Manufacturing | Issued by Caldova Pharmaceuticals

RFP Reference: CALDOVA-RFP-2026-ALV-001 (RFQ 000010)

Response Date: June 15, 2026

Contact: Thomas Reyes, Director of Business Development

Email: t.reyes@annterra-pharma.com

# Cover Letter

Dear Caldova Pharmaceuticals Sourcing Committee,

Annterra Pharma is pleased to submit this formal response to your Request for Proposal for contract manufacturing of Allerveo 180mg tablets. We have reviewed your requirements in detail and built this proposal around the quality expectations, documentation standards, and supply pace that a program of this profile demands.

Quality and reliability are the foundation of this offer. Our most recent FDA inspection closed with a No Action Indicated outcome — our third consecutive NAI — and we carry zero open regulatory actions. Across the trailing twelve months our on-time-in-full performance is 97.2% and our batch rejection rate is 0.8%, with a right-first-time rate of 98.1%. Our last five technology transfers have completed on plan, a 100% first-pass success record.

We also bring capacity certainty. Our new oral solid dose line comes online this summer, taking our network to 850,000 units per month with approximately 580,000 units unallocated. Your program's 50,000 units per month commitment is absorbed without stressing utilization, protecting quality metrics at volume.

We are pleased to extend our preferred customer rate for this program. We are confident that no respondent offers a stronger combination of regulatory standing, delivery reliability, and executable ramp plan, and we welcome the opportunity to discuss this proposal with your team.

Respectfully submitted,

Thomas Reyes

Director of Business Development, Annterra Pharma

# Bid Summary

| Item | Detail |
| --- | --- |
| Proposed Unit Price | $4.85 (preferred customer rate) |
| Lead Time to First Commercial Batch | 14 weeks from contract execution |
| First Commercial Delivery | Week 14 — target receipt September 8, 2026 |
| Monthly Capacity Commitment | 50,000 units confirmed |
| Minimum Order Quantity | 100,000 units per batch |
| Volume Price Step-Down | $4.60 per unit from month 13 (blended contract rate ~$4.68) |
| Engineering Batch | Charged at cost, fully credited against the first commercial order |
| Payment Terms | Net 90 |
| Expedited Option | Week-13 first delivery available at no charge via pre-booked materials |
| Proposed Contract Term | 3 years, price held flat for the full term |

# Program Execution Timeline

Our proposed 14-week execution plan from contract execution to first commercial delivery, organized in four phases. Each milestone is owned by a named program lead and reported weekly to Caldova.

| Phase | Milestone | Weeks |
| --- | --- | --- |
| Setup & Alignment | Contract execution & kickoff | Week 0 |
| Setup & Alignment | Technical & quality alignment | Weeks 1–2 |
| Sourcing & Scheduling | Material planning & procurement | Weeks 2–4 |
| Sourcing & Scheduling | Line scheduling & readiness | Weeks 4–6 |
| Manufacturing | Engineering / confirmation batch | Weeks 6–8 |
| Manufacturing | First commercial batch manufacture | Weeks 8–10 |
| Testing & Delivery | Quality testing & release | Weeks 10–12 |
| Testing & Delivery | Packaging, shipment & delivery — first commercial delivery | Weeks 12–14 |

Final delivery milestone: first commercial delivery in week 14, against a target receipt date of September 8, 2026.

# Partnership & Account Performance

We submit our verified account-performance record from our most recent long-term commercial OSD program (18 months, reference client available under NDA) as part of this response:

| Measure | Most recent 18-month commercial OSD program |
| --- | --- |
| On-time-in-full to client | 100% — zero late or short shipments |
| Batch rejections on client product | Zero |
| Query / issue response time | Under 24 hours, contractual SLA — measured average 6 business hours |
| Governance | Named program manager, dedicated account team, weekly S&OP integration with client planning, quarterly business reviews with executive sponsor |
| Escalation performance | Both program escalations resolved within 48 hours with corrective actions accepted by the client's quality organization |

The same named program manager and account team are committed to this Allerveo program from day one. Client references available on request.

# Appendix A - Questionnaire Responses

## Section 1 - Regulatory and GMP

Q1: GMP certification status and most recent site inspection outcome.

GMP certified for oral solid dose production across the network, including the new line commissioning this summer. Most recent inspection: No Action Indicated (NAI), completed February 2026 — our third consecutive NAI outcome. GMP certificates enclosed.

Q2: Details of all regulatory inspections in the past five years.

February 2026, FDA, NAI. 2024, FDA, NAI. 2022, FDA, NAI. No observations issued in any of the three inspections. Full inspection histories available on request.

Q3: Disclosure of any open regulatory actions, warning letters, or consent decrees.

No open regulatory actions. No warning letters or consent decrees in effect, and none in company history.

## Section 2 - Quality Systems

Q1: Batch rejection rate for oral solid dose products over the most recent 12-month period.

Batch rejection rate for OSD products: 0.8% (trailing 12 months). Right-first-time rate: 98.1%.

Q2: Describe your deviation management and CAPA process, including average closure times.

Deviations are managed under a single global quality management system with electronic batch records. Average CAPA closure time: 18 days. Trend reviews are conducted monthly and shared with clients under quality agreement.

Q3: Confirm willingness to execute a quality agreement and provide a draft framework.

Confirmed. Our standard quality agreement framework is enclosed; we are equally comfortable executing on Caldova's paper.

## Section 3 - Capacity and Supply

Q1: Confirm available monthly capacity and lead time to first commercial batch for this program.

Network capacity: 850,000 units per month following the OSD expansion coming online this summer, with approximately 580,000 units per month unallocated (network utilization approximately 68%). We confirm 50,000 units per month for this program, with first commercial batch released within 14 weeks of contract execution and first delivery targeted for receipt September 8, 2026.

Q2: Describe your backup manufacturing arrangements and business continuity plan.

Dual-line redundancy within the network for all OSD processes; validated transfer packages allow production to shift between lines without regulatory refiling. Formal business continuity plan enclosed.

Q3: Confirm serialization and track-and-trace capabilities.

Full serialization and aggregation in production at all packaging lines, compliant with DSCSA and EU FMD. Direct integration available to Caldova's track-and-trace provider.

## Section 4 - Commercial and Risk

Q1: Company background, ownership structure, and financial stability.

Annterra Pharma has operated in commercial OSD contract manufacturing for 25 years from our New Jersey, USA headquarters site. Privately held with stable ownership. Financial stability rating: A+.

Q2: Disclose any subcontracting arrangements for manufacturing steps.

No subcontracting of any manufacturing, testing, or packaging steps. All operations performed at Annterra-owned facilities.

Q3: Describe your client relationship model and provide references.

Every program is assigned a named program manager and dedicated account team with a contractual 24-hour response SLA, weekly S&OP integration and quarterly business reviews. References: three long-term commercial OSD clients enclosed, including an 18-month program completed with 100% OTIF and zero batch rejections.

Q4: Provide details of product liability and professional indemnity insurance coverage.

Product liability coverage: $50M. Professional indemnity: $20M. Certificates enclosed. Technology transfer performance: 5 of 5 most recent transfers completed on plan (100% first-pass success).

| Thomas Reyes ¦ Director of Business Development ¦ Annterra Pharma ¦ t.reyes@annterra-pharma.com ¦ +1 (973) 555-0148 |  |
| --- | --- |